## Design_Build Spreadsheet
Client Name: | [5 empty] | Project Manager:
Project ID: | [5 empty] | Start Date:
Tips on Using This Spreadsheet:
- | This spreadsheet identifies key steps toward the successful completion of a design / build project, assigns responsibility to the appropriate
parties and establishes timing. While your company may not have separate Sales, Design, Production and Administrative departments,
adapt this spreadsheet and assign responsibility appropriately.
- | Consistent use of this spreadsheet enables your company to successfully track:
1. Strengths, weaknesses and opportunities for improvement for each business function.
2. Your company's effectiveness within each aspect of the design / build process.
3. Timing Variance: Are you hitting your target dates? Which aspects of your approach may be modified to be more effective?
# | Function |  |  | Responsible Party |  |  |  | Target | Revised | Actual
|  |  |  | Sales | Design | Prod | Admin | Date | Date | Date
1 | Initial Meeting
|  | Client-Contractor Interview |  | X
|  | Project Overview By Priority |  | X
|  | Budget Discussion vs. General Costs vs. Value |  | X
|  | Discussion on Design - Build Process |  | X | X
|  | Design Choice and Costs of Services Options |  | X | X
Architect
Designer
Design by Contractor
|  | Interior Decorator Services / Fees |  | X
|  | Industry Standards (Residential Construction) |  | X
|  | Client living requirements during Construction |  | X
2 | Design Meeting
|  | Intro & Qualifications of Architect or Designer |  | X | X
|  | Discuss Project Overview and Budget |  | X | X
|  | Discuss Project Priorities & Special Interests |  | X | X
|  | Discuss Fees and Design Agreement |  | X | X
3 | Design Agreement Meeting
|  | Read, Discuss and sign Design Agreement |  | X
|  | Establish Design Program w/ Architect |  | X | X
4 | Field Measurement Design
|  | Field measure home for Preliminary Drawings |  |  | X | X
|  | Determine requirement for new Survey of Lot |  |  | X | X
Client Name: | [5 empty] | Project Manager:
Project ID: | [5 empty] | Start Date:
# | Function |  |  | Responsible Party |  |  |  | Target | Revised | Actual
|  |  |  | Sales | Design | Prod | Admin | Date | Date | Date
5 | Preliminary Drawing Submission to Client
|  | Discuss and finalize Preliminary Design |  | X | X
|  | Provide Contractor with copy of design |  |  |  |  | X
6 | Preliminary Design Detail Meeting
|  | Architect, Contractor, Client review plans |  |  | X | X
7 | Prepare & Submit Preliminary Design Cost Estimate
|  | Obtain estimates from subcontractors on design |  |  |  |  | X
|  | Discuss Preliminary Costs vs. Budget |  | X
|  | Make required changes |  | X | X
|  | Discuss allowances |  | X
|  | Provide Client with Product Selection Guide |  | X
8 | Prepare Construction Drawings
|  | Client begins to make Product Selections |  | X | X
9 | Prepare & Submit Final Project Bid
|  | Subcontractors provide final bids for final drawings |  | X |  |  | X
|  | Determine final cost on product allowances or selections |  | X | X
|  | Review drawings and costs with Client |  | X | X
|  | Review and finalize scope of work narrative |  | X | X | X
10 | Financing Procedures
Loan Application
|  | Submit bid and drawings to Lender |  |  |  |  | X
Loan Approval
|  | Set appointment for closing of loan |  | X
|  | Set appointment for signing of Contractor Contract |  | X
|  | Submit Disclosure Statement to Client for signature |  | X |  |  | X
11 | Contract & Loan Completion
|  | Loan & Contract signed at financing Institution |  | X
|  | Contractor submit Vender and Subcontractor lists |  |  |  | X
Client Name: | [5 empty] | Project Manager:
Project ID: | [5 empty] | Start Date:
# | Function |  |  | Responsible Party |  |  |  | Target | Revised | Actual
|  |  |  | Sales | Design | Prod | Admin | Date | Date | Date
12 | Pre-Construction Preparation
|  | Apply for relevant Permits |  |  |  |  | X
|  | Product Selection Guide to be completed by Client |  | X
|  | Hand-off bid package to Production |  | X |  | X | X
Pre-construction Meeting
|  | Create decision / benchmark checklist |  | X |  | X
13 | Site Preparation & Demolition
|  | Start Prep & Demolition |  |  |  | X
|  | Complete Prep & Demolition |  |  |  | X
14 | Initiate Shop Drawings |  |  |  |  | X
|  | Submit first draw invoice and obtain payment |  |  |  |  | X
15 | Mid Construction Meeting |  |  | X | X | X
16 | Punchlist Completion |  |  |  |  | X
17 | Final Invoice | [5 empty] | X
18 | Project Closure Visit & Gift
|  | Post Construction Job Review |  | X | X | X | X
|  | Archive files and set up photo shoot |  |  | X |  | X